## MatLabCategoryVarianceSummary63
Material/Labour Category Variance Summary
Project Name : Vrundavan Elysia
Task Name : RCC
Page 1 of 1
Total Records: 19 Records 1 to 19
Sr_No | Category_Name | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | GRN_Qty | Issue_RABill_Qty_3 | Issue_RABill_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3)
1 | MP1-READY MIX CONCRETE | (M)M 25 | CMT | 212 | 4720 | 1000640 | 35.75 | 35.75 | 4250.18 | 151943.88 | 33.5 | 140.25 | 4267.3 | 598488.36 | 176.25 | 71.75 | 848696.12 | 402151.64
2 | MP1-READY MIX CONCRETE | (M)M 25 Pumping | CMT | 2109 | 4729.62 | 9974776 | 1889 | 1889 | 4366.94 | 8249148.72 | 1781 | 1803.5 | 4352.52 | 7849777 | 220 | 305.5 | 1725627.28 | 2124999
3 | MP1-READY MIX CONCRETE | (M)M 35 dumping | CMT | 562.7736 | 6254 | 3519586.09 | 562.7736 | 562.7736 | 4525.83 | 2547016.26 | 551.21 | 540 | 4523.74 | 2442818.64 | 0 | 22.7736 | 972569.83 | 1076767.45
4 | Rebar Coupling | (M)16mm coupler | NOS | 3539 | 29.5 | 104400.5 | 3507 | 3507 | 28.32 | 99318.24 | 3507 | 3880 | 28.32 | 109881.6 | 32 | -341 | 5082.26 | -5481.1
5 | Rebar Coupling | (M)16mm threading | NOS | 8010 | 11.8 | 94518 | 6946 | 6946 | 9 | 62514 | 6946 | 7426 | 9 | 66834 | 1064 | 584 | 32004 | 27684
6 | Rebar Coupling | (M)20*16mm reducing coupler | NOS | 1022 | 41.3 | 42208.6 | 900 | 900 | 41.3 | 37170 | 900 | 1216 | 41.3 | 50220.8 | 122 | -194 | 5038.6 | -8012.2
7 | Rebar Coupling | (M)20mm coupler | NOS | 1672 | 41.3 | 69053.6 | 1512 | 1512 | 41.3 | 62445.6 | 1512 | 1647 | 41.3 | 68021.1 | 160 | 25 | 6608 | 1032.5
8 | Rebar Coupling | (M)20mm threading | NOS | 4890 | 17.7 | 86553 | 4224 | 4224 | 13 | 54912 | 4224 | 3253 | 13 | 42289 | 666 | 1637 | 31641 | 44264
9 | Rebar Coupling | (M)25*16mm reducing coupler | NOS | 16 | 59 | 944 | 16 | 16 | 59 | 944 | 16 | 10 | 59 | 590 | 0 | 6 | 0 | 354
10 | Rebar Coupling | (M)25*20mm reducing coupler | NOS | 560 | 59 | 33040 | 560 | 560 | 59 | 33040 | 560 | 668 | 59 | 39412 | 0 | -108 | 0 | -6372
11 | Rebar Coupling | (M)25mm coupler | NOS | 984 | 59 | 58056 | 768 | 768 | 59 | 45312 | 768 | 1024 | 59 | 60416 | 216 | -40 | 12744 | -2360
12 | Rebar Coupling | (M)25mm threading | NOS | 2544 | 23.6 | 60038.4 | 2462 | 2462 | 15 | 36930 | 2462 | 1736 | 15 | 26040 | 82 | 808 | 23108.4 | 33998.4
13 | Steel | (M)10 MM TMT Bars | TON | 138.638 | 62334.02 | 8641864.52 | 126.538 | 126.538 | 59733.89 | 7558607.48 | 126.538 | 120.782 | 60262.23 | 7278592.71 | 12.1 | 17.856 | 1083257.04 | 1363271.81
14 | Steel | (M)12 MM TMT Bars | TON | 38.53 | 62540 | 2409666.2 | 36.09 | 36.09 | 59200.1 | 2136531.49 | 36.09 | 36.75 | 58774.78 | 2159973.25 | 2.44 | 1.78 | 273134.71 | 249692.95
15 | Steel | (M)16 MM TMT Bars | TON | 74.97 | 62540 | 4688623.8 | 68.12 | 68.12 | 58410.32 | 3978910.79 | 68.12 | 63.46 | 58542.61 | 3715114.25 | 6.85 | 11.51 | 709713.01 | 973509.55
16 | Steel | (M)20 MM TMT Bars | TON | 49.12 | 62540 | 3071964.8 | 44.71 | 44.71 | 58835.76 | 2630546.93 | 44.71 | 44.73 | 58835.11 | 2631694.44 | 4.41 | 4.39 | 441417.87 | 440270.36
17 | Steel | (M)25 MM TMT Bars | TON | 58.33 | 62540 | 3647958.2 | 47.7 | 47.7 | 59528.31 | 2839500.27 | 47.7 | 39.1276 | 59754.82 | 2338062.89 | 10.63 | 19.2024 | 808457.93 | 1309895.31
18 | Steel | (M)8 MM TMT Bars | TON | 132.792 | 62000 | 8233104 | 132.232 | 132.232 | 60970.53 | 8062255.66 | 132.232 | 125.872 | 61192.54 | 7702426.8 | 0.56 | 6.92 | 170848.34 | 530677.2
19 | RCC | (L)RCC Labour | sq.ft | 103054 | 218.3 | 22496688.2 | 0 | 22831.3 | 218.3 | 4984072.8 | 22831.3 | 22831.3 | 218.3 | 4984072.8 | 80222.7 | 80222.7 | 17512615.4 | 17512615.4