## MatLabCategoryVarianceSummary63
Material/Labour Category Variance Summary
Project Name : Vrundavan Elysia
Task Name : RCC
Page 1 of 1
Total Records: 20 Records 1 to 20
Sr_No | Category_Name | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | GRN_Qty | Issue_RABill_Qty_3 | Issue_RABill_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3)
1 | MP1-READY MIX CONCRETE | (M)M 25 | CMT | 227 | 4720 | 1071440 | 95 | 95 | 4313.58 | 409790.4 | 35 | 104.25 | 4235.49 | 441549.52 | 132 | 122.75 | 661649.6 | 629890.48
2 | MP1-READY MIX CONCRETE | (M)M 25 Pumping | CMT | 1956 | 4729.71 | 9251318 | 1726 | 1726 | 4366.86 | 7537207.52 | 1726 | 1822.21 | 4364.7 | 7953402.42 | 230 | 133.79 | 1714110.48 | 1297915.58
3 | MP1-READY MIX CONCRETE | (M)M 35 dumping | CMT | 517.61 | 6254 | 3237132.94 | 517.61 | 517.61 | 4527.95 | 2343713.56 | 517.61 | 448.68 | 4530.47 | 2032732.13 | 0 | 68.93 | 893419.38 | 1204400.81
4 | Rebar Coupling | (M)16mm coupler | NOS | 3133 | 29.5 | 92423.5 | 2925 | 2925 | 28.32 | 82836 | 2925 | 2919 | 28.32 | 82666.08 | 208 | 214 | 9587.5 | 9757.42
5 | Rebar Coupling | (M)16mm threading | NOS | 7085 | 11.8 | 83603 | 6226 | 6226 | 9 | 56034 | 6226 | 5386 | 9 | 48474 | 859 | 1699 | 27569 | 35129
6 | Rebar Coupling | (M)20*16mm reducing coupler | NOS | 811 | 41.3 | 33494.3 | 800 | 800 | 41.3 | 33040 | 800 | 718 | 41.3 | 29653.4 | 11 | 93 | 454.3 | 3840.9
7 | Rebar Coupling | (M)20mm coupler | NOS | 2044 | 41.3 | 84417.2 | 1862 | 1862 | 41.3 | 76900.6 | 1862 | 1612 | 41.3 | 66575.6 | 182 | 432 | 7516.6 | 17841.6
8 | Rebar Coupling | (M)20mm threading | NOS | 5367 | 17.7 | 94995.9 | 4560 | 4560 | 13 | 59280 | 4560 | 2988 | 13 | 38844 | 807 | 2379 | 35715.9 | 56151.9
9 | Rebar Coupling | (M)25*16mm reducing coupler | NOS | 24 | 31.47 | 755.2 | 16 | 16 | 59 | 944 | 16 | 10 | 59 | 590 | 8 | 14 | -188.8 | 165.2
10 | Rebar Coupling | (M)25*20mm reducing coupler | NOS | 468 | 59 | 27612 | 468 | 468 | 59 | 27612 | 468 | 521 | 59 | 30739 | 0 | -53 | 0 | -3127
11 | Rebar Coupling | (M)25mm coupler | NOS | 876 | 59 | 51684 | 596 | 596 | 59 | 35164 | 596 | 614 | 59 | 36226 | 280 | 262 | 16520 | 15458
12 | Rebar Coupling | (M)25mm threading | NOS | 2244 | 23.6 | 52958.4 | 1547 | 1547 | 15 | 23205 | 1547 | 592 | 15 | 8880 | 697 | 1652 | 29753.4 | 44078.4
13 | Steel | (M)10 MM TMT Bars | TON | 126.435 | 62312.65 | 7878500.1 | 121.103 | 121.103 | 59305.35 | 7182055.99 | 121.103 | 123.47 | 59234.69 | 7313707.33 | 5.332 | 2.965 | 696444.11 | 564792.77
14 | Steel | (M)12 MM TMT Bars | TON | 37.545 | 62540 | 2348064.3 | 28.59 | 28.59 | 58698.57 | 1678192.04 | 28.59 | 37.59 | 58357.22 | 2193647.77 | 8.955 | -0.045 | 669872.26 | 154416.53
15 | Steel | (M)16 MM TMT Bars | TON | 73.29 | 62540 | 4583556.6 | 63.88 | 63.88 | 58319.26 | 3725434.04 | 63.88 | 58.159 | 58757.16 | 3417257.8 | 9.41 | 15.131 | 858122.56 | 1166298.8
16 | Steel | (M)20 MM TMT Bars | TON | 79.865 | 62540 | 4994757.1 | 74.96 | 74.96 | 57841.89 | 4335828.4 | 74.96 | 65.88 | 58318.55 | 3842026 | 4.905 | 13.985 | 658928.7 | 1152731.1
17 | Steel | (M)25 MM TMT Bars | TON | 51.985 | 62540 | 3251141.9 | 50.79 | 50.79 | 58451.15 | 2968733.85 | 50.79 | 45.3424 | 58731.76 | 2663039.01 | 1.195 | 6.6426 | 282408.05 | 588102.89
18 | Steel | (M)32 MM TMT Bars | TON | 0.39 | 62540 | 24390.6 | 0.37 | 0.37 | 59399.99 | 21978 | 0.37 | 0.39 | 59400 | 23166 | 0.02 | 0 | 2412.6 | 1224.6
19 | Steel | (M)8 MM TMT Bars | TON | 124.805 | 62000 | 7737910 | 121.4 | 121.4 | 60587.97 | 7355379.53 | 121.4 | 124.655 | 60763.24 | 7574441.82 | 3.405 | 0.15 | 382530.47 | 163468.18
20 | RCC | (L)RCC Labour | sq.ft | 100707.5 | 218.3 | 21984447.25 | 0 | 14734.43 | 218.3 | 3216526.07 | 14734.43 | 14734.43 | 218.3 | 3216526.07 | 85973.07 | 85973.07 | 18767921.18 | 18767921.18