## MatLabCategoryVarianceSummary63
Material/Labour Category Variance Summary
Project Name : Vrundavan Elysia
Task Name : RCC
Page 1 of 1
Total Records: 20 Records 1 to 20
Sr_No | Category_Name | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | GRN_Qty | Issue_RABill_Qty_3 | Issue_RABill_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3)
1 | MP1-READY MIX CONCRETE | (M)M 25 | CMT | 227 | 4720 | 1071440 | 95 | 95 | 4313.58 | 409790.4 | 76.75 | 93 | 4279.54 | 397997.48 | 132 | 134 | 661649.6 | 673442.52
2 | MP1-READY MIX CONCRETE | (M)M 25 Pumping | CMT | 1970 | 4729.64 | 9317398 | 1726 | 1726 | 4373.22 | 7548172.27 | 1705.5 | 1670.5 | 4372.41 | 7304102.61 | 244 | 299.5 | 1769225.73 | 2013295.39
3 | MP1-READY MIX CONCRETE | (M)M 35 dumping | CMT | 517.03 | 6254 | 3233505.62 | 481.69 | 481.69 | 4527.39 | 2180799.3 | 481.69 | 497.32 | 4532.98 | 2254339.94 | 35.34 | 19.71 | 1052706.32 | 979165.68
4 | Rebar Coupling | (M)16mm coupler | NOS | 3133 | 29.5 | 92423.5 | 2909 | 2909 | 28.32 | 82382.88 | 2909 | 2937 | 28.32 | 83175.84 | 224 | 196 | 10040.62 | 9247.66
5 | Rebar Coupling | (M)16mm threading | NOS | 7085 | 11.8 | 83603 | 5736 | 5736 | 9 | 51624 | 5736 | 6298 | 9 | 56682 | 1349 | 787 | 31979 | 26921
6 | Rebar Coupling | (M)20*16mm reducing coupler | NOS | 811 | 41.3 | 33494.3 | 700 | 700 | 41.3 | 28910 | 700 | 390 | 41.3 | 16107 | 111 | 421 | 4584.3 | 17387.3
7 | Rebar Coupling | (M)20mm coupler | NOS | 2044 | 41.3 | 84417.2 | 1777 | 1777 | 41.3 | 73390.1 | 1777 | 1438 | 41.3 | 59389.4 | 267 | 606 | 11027.1 | 25027.8
8 | Rebar Coupling | (M)20mm threading | NOS | 5367 | 17.7 | 94995.9 | 4372 | 4372 | 13 | 56836 | 4372 | 3492 | 13 | 45396 | 995 | 1875 | 38159.9 | 49599.9
9 | Rebar Coupling | (M)25*16mm reducing coupler | NOS | 24 | 31.47 | 755.2 | 16 | 16 | 59 | 944 | 16 | 28 | 59 | 1652 | 8 | -4 | -188.8 | -896.8
10 | Rebar Coupling | (M)25*20mm reducing coupler | NOS | 468 | 59 | 27612 | 468 | 468 | 59 | 27612 | 468 | 376 | 59 | 22184 | 0 | 92 | 0 | 5428
11 | Rebar Coupling | (M)25mm coupler | NOS | 876 | 59 | 51684 | 468 | 468 | 59 | 27612 | 468 | 554 | 59 | 32686 | 408 | 322 | 24072 | 18998
12 | Rebar Coupling | (M)25mm threading | NOS | 2244 | 23.6 | 52958.4 | 1551 | 1551 | 15 | 23265 | 1551 | 252 | 15 | 3780 | 693 | 1992 | 29693.4 | 49178.4
13 | Steel | (M)10 MM TMT Bars | TON | 126.835 | 62313.37 | 7903516.1 | 97.975 | 97.975 | 60053.55 | 5883746.99 | 97.975 | 95.8219 | 59462.99 | 5697856.88 | 28.86 | 31.0131 | 2019769.11 | 2205659.22
14 | Steel | (M)12 MM TMT Bars | TON | 37.395 | 62540 | 2338683.3 | 30.03 | 30.03 | 58867.08 | 1767778.52 | 30.03 | 27.007 | 58349.44 | 1575843.46 | 7.365 | 10.388 | 570904.78 | 762839.84
15 | Steel | (M)16 MM TMT Bars | TON | 73.24 | 62540 | 4580429.6 | 53.9471 | 53.9471 | 58891.02 | 3176999.7 | 53.9471 | 49.78 | 58505.18 | 2912387.95 | 19.2929 | 23.46 | 1403429.9 | 1668041.65
16 | Steel | (M)20 MM TMT Bars | TON | 78.265 | 62540 | 4894693.1 | 70.69 | 70.69 | 58466.24 | 4132978.67 | 70.69 | 43.42 | 58358.61 | 2533930.8 | 7.575 | 34.845 | 761714.43 | 2360762.3
17 | Steel | (M)25 MM TMT Bars | TON | 52.585 | 62540 | 3288665.9 | 46.75 | 46.75 | 58619.31 | 2740452.52 | 46.75 | 43.2 | 58518.49 | 2527998.71 | 5.835 | 9.385 | 548213.38 | 760667.19
18 | Steel | (M)32 MM TMT Bars | TON | 0.39 | 62540 | 24390.6 | 0.39 | 0.39 | 59399.99 | 23166 | 0.39 | 0.39 | 62271.79 | 24286 | 0 | 0 | 1224.6 | 104.6
19 | Steel | (M)8 MM TMT Bars | TON | 125.155 | 62000 | 7759610 | 113.99 | 113.99 | 60991.71 | 6952445.39 | 113.99 | 109.09 | 60515.13 | 6601595.35 | 11.165 | 16.065 | 807164.61 | 1158014.65
20 | RCC | (L)RCC Labour | sq.ft | 100708.5 | 218.3 | 21984665.55 | 0 | 21980.68 | 218.3 | 4798382.44 | 21980.68 | 21980.68 | 218.3 | 4798382.44 | 78727.82 | 78727.82 | 17186283.11 | 17186283.11