## MatLabCategoryVarianceSummary63
Material/Labour Category Variance Summary
Project Name : Vrundavan Elysia
Task Name : RCC
Page 1 of 1
Total Records: 20 Records 1 to 20
Sr_No | Category_Name | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | GRN_Qty | Issue_RABill_Qty_3 | Issue_RABill_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3)
1 | MP1-READY MIX CONCRETE | (M)M 25 | CMT | 228 | 4720 | 1076160 | 95 | 95 | 4304.02 | 408881.8 | 95 | 90 | 4248.36 | 382352.46 | 133 | 138 | 667278.2 | 693807.54
2 | MP1-READY MIX CONCRETE | (M)M 25 Pumping | CMT | 1876 | 4729.31 | 8872184 | 1653 | 1653 | 4367.02 | 7218675.96 | 1630 | 1650.375 | 4347.12 | 7174377.57 | 223 | 225.625 | 1653508.04 | 1697806.43
3 | MP1-READY MIX CONCRETE | (M)M 35 dumping | CMT | 527.995 | 6254 | 3302080.73 | 491.94 | 491.94 | 4521.65 | 2224378.61 | 490.75 | 551.75 | 4512.55 | 2489801.05 | 36.055 | -23.755 | 1077702.12 | 812279.68
4 | Rebar Coupling | (M)16mm coupler | NOS | 3529 | 29.5 | 104105.5 | 2101 | 2101 | 28.32 | 59500.32 | 2101 | 3008 | 28.32 | 85186.56 | 1428 | 521 | 44605.18 | 18918.94
5 | Rebar Coupling | (M)16mm threading | NOS | 7893 | 11.8 | 93137.4 | 6048 | 6048 | 9 | 54432 | 6048 | 7454 | 9 | 67086 | 1845 | 439 | 38705.4 | 26051.4
6 | Rebar Coupling | (M)20*16mm reducing coupler | NOS | 819 | 41.3 | 33824.7 | 728 | 728 | 41.3 | 30066.4 | 728 | 724 | 41.3 | 29901.2 | 91 | 95 | 3758.3 | 3923.5
7 | Rebar Coupling | (M)20mm coupler | NOS | 1745 | 41.3 | 72068.5 | 1709 | 1709 | 41.3 | 70581.7 | 1709 | 1170 | 41.3 | 48321 | 36 | 575 | 1486.8 | 23747.5
8 | Rebar Coupling | (M)20mm threading | NOS | 4739 | 17.7 | 83880.3 | 4531 | 4531 | 13 | 58903 | 4531 | 3916 | 13 | 50908 | 208 | 823 | 24977.3 | 32972.3
9 | Rebar Coupling | (M)25*16mm reducing coupler | NOS | 16 | 59 | 944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 944 | 944
10 | Rebar Coupling | (M)25*20mm reducing coupler | NOS | 429 | 59 | 25311 | 429 | 429 | 59 | 25311 | 429 | 421 | 59 | 24839 | 0 | 8 | 0 | 472
11 | Rebar Coupling | (M)25mm coupler | NOS | 524 | 59 | 30916 | 370 | 370 | 59 | 21830 | 370 | 571 | 59 | 33689 | 154 | -47 | 9086 | -2773
12 | Rebar Coupling | (M)25mm threading | NOS | 1493 | 23.6 | 35234.8 | 1412 | 1412 | 15 | 21180 | 1412 | 340 | 15 | 5100 | 81 | 1153 | 14054.8 | 30134.8
13 | Steel | (M)10 MM TMT Bars | TON | 113.385 | 62309.38 | 7064949.1 | 87.815 | 87.815 | 59748.98 | 5246857.05 | 85.765 | 76.405 | 59884.35 | 4575463.97 | 25.57 | 36.98 | 1818092.05 | 2489485.13
14 | Steel | (M)12 MM TMT Bars | TON | 39.89 | 62540 | 2494720.6 | 39.625 | 39.625 | 58548.56 | 2319986.86 | 39.625 | 38.995 | 58548.75 | 2283108.69 | 0.265 | 0.895 | 174733.74 | 211611.91
15 | Steel | (M)16 MM TMT Bars | TON | 71.48 | 62540 | 4470359.2 | 67.08 | 67.08 | 58398.25 | 3917354.46 | 67.08 | 35.78 | 58271.48 | 2084953.52 | 4.4 | 35.7 | 553004.74 | 2385405.68
16 | Steel | (M)20 MM TMT Bars | TON | 79.66 | 62540 | 4981936.4 | 75.22 | 75.22 | 58240.49 | 4380849.47 | 75.22 | 51.04 | 59094.62 | 3016189.31 | 4.44 | 28.62 | 601086.93 | 1965747.09
17 | Steel | (M)25 MM TMT Bars | TON | 43.645 | 62540 | 2729558.3 | 24.48 | 24.48 | 58213.48 | 1425065.98 | 24.48 | 30.98 | 59313.76 | 1837540.41 | 19.165 | 12.665 | 1304492.32 | 892017.89
18 | Steel | (M)32 MM TMT Bars | TON | 0.365 | 62540 | 22827.1 | 0.365 | 0.365 | 62899.99 | 22958.5 | 0.365 | 0.365 | 62899.97 | 22958.49 | 0 | 0 | -131.4 | -131.39
19 | Steel | (M)8 MM TMT Bars | TON | 123 | 62000 | 7626000 | 113.19 | 113.19 | 61218.54 | 6929327.02 | 113.19 | 121.82 | 61013.54 | 7432669.8 | 9.81 | 1.18 | 696672.98 | 193330.2
20 | RCC | (L)RCC Labour | sq.ft | 95154.5 | 218.3 | 20772227.35 | 0 | 69026.78 | 185 | 12769954.3 | 59286.78 | 59286.78 | 185 | 10968054.3 | 26127.72 | 35867.72 | 8002273.05 | 9804173.05