## MatLabCategoryVarianceSummary63
Material/Labour Category Variance Summary
Project Name : Vrundavan Elysia
Task Name : RCC
Page 1 of 1
Total Records: 20 Records 1 to 20
Sr_No | Category_Name | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | GRN_Qty | Issue_RABill_Qty_3 | Issue_RABill_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3)
1 | MP1-READY MIX CONCRETE | (M)M 25 | CMT | 228 | 4720 | 1076160 | 95 | 95 | 4313.58 | 409790.4 | 95 | 56.26 | 4234.72 | 238245.38 | 133 | 171.74 | 666369.6 | 837914.62
2 | MP1-READY MIX CONCRETE | (M)M 25 Pumping | CMT | 1876 | 4729.31 | 8872184 | 1653 | 1653 | 4367.02 | 7218675.96 | 1643.25 | 1626.375 | 4374.06 | 7113861.61 | 223 | 249.625 | 1653508.04 | 1758322.39
3 | MP1-READY MIX CONCRETE | (M)M 35 dumping | CMT | 527.995 | 6254 | 3302080.73 | 491.94 | 491.94 | 4521.65 | 2224378.61 | 491.11 | 500.25 | 4527.15 | 2264707.35 | 36.055 | 27.745 | 1077702.12 | 1037373.38
4 | Rebar Coupling | (M)16mm coupler | NOS | 3529 | 29.5 | 104105.5 | 2257 | 2257 | 28.32 | 63918.24 | 2257 | 963 | 28.32 | 27272.16 | 1272 | 2566 | 40187.26 | 76833.34
5 | Rebar Coupling | (M)16mm threading | NOS | 7893 | 11.8 | 93137.4 | 5248 | 5248 | 9 | 47232 | 5248 | 3640 | 9 | 32760 | 2645 | 4253 | 45905.4 | 60377.4
6 | Rebar Coupling | (M)20*16mm reducing coupler | NOS | 819 | 41.3 | 33824.7 | 723 | 723 | 41.3 | 29859.9 | 723 | 250 | 41.3 | 10325 | 96 | 569 | 3964.8 | 23499.7
7 | Rebar Coupling | (M)20mm coupler | NOS | 1745 | 41.3 | 72068.5 | 1687 | 1687 | 41.3 | 69673.1 | 1687 | 610 | 41.3 | 25193 | 58 | 1135 | 2395.4 | 46875.5
8 | Rebar Coupling | (M)20mm threading | NOS | 4738 | 17.7 | 83862.6 | 4738 | 4738 | 13 | 61594 | 4738 | 2210 | 13 | 28730 | 0 | 2528 | 22268.6 | 55132.6
9 | Rebar Coupling | (M)25*16mm reducing coupler | NOS | 16 | 59 | 944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 944 | 944
10 | Rebar Coupling | (M)25*20mm reducing coupler | NOS | 429 | 59 | 25311 | 429 | 429 | 59 | 25311 | 429 | 368 | 59 | 21712 | 0 | 61 | 0 | 3599
11 | Rebar Coupling | (M)25mm coupler | NOS | 539 | 59 | 31801 | 430 | 430 | 59 | 25370 | 430 | 61 | 59 | 3599 | 109 | 478 | 6431 | 28202
12 | Rebar Coupling | (M)25mm threading | NOS | 1492 | 23.6 | 35211.2 | 990 | 990 | 15 | 14850 | 990 | 0 | 0 | 0 | 502 | 1492 | 20361.2 | 35211.2
13 | Steel | (M)10 MM TMT Bars | TON | 113.335 | 62309.28 | 7061822.1 | 77.489 | 77.489 | 60004.21 | 4649666.16 | 77.489 | 89.005 | 60155.87 | 5354172.86 | 35.846 | 24.33 | 2412155.94 | 1707649.24
14 | Steel | (M)12 MM TMT Bars | TON | 39.89 | 62540 | 2494720.6 | 37.365 | 37.365 | 58674.75 | 2192381.96 | 37.365 | 42.51 | 58542.29 | 2488632.63 | 2.525 | -2.62 | 302338.64 | 6087.97
15 | Steel | (M)16 MM TMT Bars | TON | 71.485 | 62540 | 4470671.9 | 66.325 | 66.325 | 58514.31 | 3880961.74 | 66.325 | 66.76 | 58679.45 | 3917440.22 | 5.16 | 4.725 | 589710.16 | 553231.68
16 | Steel | (M)20 MM TMT Bars | TON | 79.56 | 62540 | 4975682.4 | 63.19 | 63.19 | 58717.78 | 3710376.8 | 63.19 | 73.37 | 58585.07 | 4298386.36 | 16.37 | 6.19 | 1265305.6 | 677296.04
17 | Steel | (M)25 MM TMT Bars | TON | 43.645 | 62540 | 2729558.3 | 25.84 | 25.84 | 59406.61 | 1535066.92 | 25.84 | 34.84 | 58690.07 | 2044762.09 | 17.805 | 8.805 | 1194491.38 | 684796.21
18 | Steel | (M)32 MM TMT Bars | TON | 0.365 | 62540 | 22827.1 | 0.365 | 0.365 | 62899.99 | 22958.5 | 0.365 | 0.365 | 62900 | 22958.5 | 0 | 0 | -131.4 | -131.4
19 | Steel | (M)8 MM TMT Bars | TON | 123.04 | 62000 | 7628480 | 112.23 | 112.23 | 60999.67 | 6845993.34 | 112.23 | 102.11 | 61490.73 | 6278818.42 | 10.81 | 20.93 | 782486.66 | 1349661.58
20 | RCC | (L)RCC Labour | sq.ft | 95153.5 | 218.3 | 20772009.05 | 0 | 42947.26 | 186.03 | 7989643.1 | 37176.26 | 37176.26 | 186.19 | 6922008.1 | 52206.24 | 57977.24 | 12782365.95 | 13850000.95