## MatLabCategoryVarianceSummary63
Material/Labour Category Variance Summary
Project Name : Vrundavan Elysia
Task Name : RCC Work
Page 1 of 1
Total Records: 36 Records 1 to 36
Sr_No | Category_Name | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | GRN_Qty | Issue_RABill_Qty_3 | Issue_RABill_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3)
1 | Cement | (M)Cement OPC 53 | BAG | 400 | 396.8 | 158720 | 400 | 400 | 402.24 | 160894.45 | 400 | 412 | 407.6 | 167931.41 | 0 | -12 | -2174.45 | -9211.41
2 | Construction Chemical | (M)Dr fixit Epoxy bonding agent | KG | 200 | 1003 | 200600 | 162 | 162 | 861.13 | 139502.29 | 162 | 156 | 860.72 | 134272.67 | 38 | 44 | 61097.71 | 66327.33
3 | Construction Chemical | (M)Dr. fixit super latex (20kg) | NOS | 4 | 5310 | 21240 | 2 | 2 | 5173.12 | 10346.24 | 2 | 2 | 5173.12 | 10346.24 | 2 | 2 | 10893.76 | 10893.76
4 | Construction Chemical | (M)MICROKRETE 40 kg. | BAG | 15 | 639.56 | 9593.4 | 15 | 15 | 610 | 9150.01 | 15 | 0 | 0 | 0 | 0 | 15 | 443.39 | 9593.4
5 | Metal Stone | (M)metal rubble stones | TON | 67 | 703.5 | 47134.5 | 65.4 | 65.4 | 689.91 | 45120.28 | 65.4 | 66.58 | 689.56 | 45910.88 | 1.6 | 0.42 | 2014.22 | 1223.62
6 | MP1-READY MIX CONCRETE | (M)M 10 | CMT | 1740 | 3540 | 6159600 | 1072 | 1072 | 3363.56 | 3605732.55 | 1071.5 | 1102.507 | 3368.48 | 3713773.57 | 668 | 637.493 | 2553867.45 | 2445826.43
7 | MP1-READY MIX CONCRETE | (M)M 20 | CMT | 1178.3921 | 4189 | 4936284.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1178.3921 | 1178.3921 | 4936284.51 | 4936284.51
8 | MP1-READY MIX CONCRETE | (M)M 25 | CMT | 1280 | 4720 | 6041600 | 1280 | 1280 | 4179.88 | 5350242.88 | 1268.5 | 1172.49 | 4203.58 | 4928656.11 | 0 | 107.51 | 691357.12 | 1112943.89
9 | MP1-READY MIX CONCRETE | (M)M 25 Pumping | CMT | 8050 | 4715.31 | 37958240 | 8050 | 8050 | 4265.47 | 34337051.78 | 7997 | 7910 | 4270.07 | 33776255.66 | 0 | 140 | 3621188.22 | 4181984.34
10 | MP1-READY MIX CONCRETE | (M)M 35 | CMT | 1245.7 | 5900 | 7349630 | 1239.1 | 1239.1 | 4478.5 | 5549309.69 | 1199.25 | 1199.25 | 4479.22 | 5371704.25 | 6.6 | 46.45 | 1800320.31 | 1977925.75
11 | MP1-READY MIX CONCRETE | (M)M 35 dumping | CMT | 5.9 | 6254 | 36898.6 | 5.9 | 5.9 | 4456.86 | 26295.47 | 5.63 | 0 | 0 | 0 | 0 | 5.9 | 10603.13 | 36898.6
12 | Rebar Coupling | (M)16mm coupler | NOS | 4170 | 38.35 | 159919.5 | 4170 | 4170 | 28.32 | 118094.4 | 4170 | 4162 | 28.32 | 117867.84 | 0 | 8 | 41825.1 | 42051.66
13 | Rebar Coupling | (M)16mm threading | NOS | 8342 | 11.8 | 98435.6 | 8340 | 8340 | 9 | 75060 | 8340 | 8340 | 9 | 75060 | 2 | 2 | 23375.6 | 23375.6
14 | Rebar Coupling | (M)20*16mm reducing coupler | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 553 | 41.3 | 22838.9 | 0 | -553 | 0 | -22838.9
15 | Rebar Coupling | (M)20mm coupler | NOS | 8430 | 52.51 | 442677 | 5885 | 5885 | 41.3 | 243050.5 | 5885 | 7955 | 41.3 | 328541.5 | 2545 | 475 | 199626.5 | 114135.5
16 | Rebar Coupling | (M)20mm threading | NOS | 16848 | 17.7 | 298209.6 | 10769 | 10769 | 13 | 139997 | 10769 | 17335 | 13 | 225355 | 6079 | -487 | 158212.6 | 72854.6
17 | Rebar Coupling | (M)25*16mm reducing coupler | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Rebar Coupling | (M)25*20mm reducing coupler | NOS | 8 | 59 | 472 | 8 | 8 | 59 | 472 | 8 | 8 | 59 | 472 | 0 | 0 | 0 | 0
19 | Rebar Coupling | (M)25mm coupler | NOS | 8204 | 80.59 | 661154 | 6890 | 6890 | 59 | 406510 | 6890 | 6700 | 59 | 395300 | 1314 | 1504 | 254644 | 265854
20 | Rebar Coupling | (M)25mm threading | NOS | 16416 | 23.6 | 387417.6 | 10922 | 10922 | 15 | 163830 | 10922 | 15964 | 15 | 239460 | 5494 | 452 | 223587.6 | 147957.6
21 | RMC | (M)M 35 Pumping | CMT | 100 | 6136 | 613600 | 100 | 100 | 4563.06 | 456306 | 80 | 80 | 4563.06 | 365044.8 | 0 | 20 | 157294 | 248555.2
22 | Steel | (M)10 MM TMT Bars | TON | 328.26 | 62540 | 20529380.4 | 299.57 | 299.57 | 62106.17 | 18605146.11 | 299.51 | 303.56 | 62037.66 | 18832153.51 | 28.69 | 24.7 | 1924234.29 | 1697226.89
23 | Steel | (M)12 MM TMT Bars | TON | 91 | 62540 | 5691140 | 89.89 | 89.89 | 60879.62 | 5472469.22 | 89.84 | 61.81 | 62370.04 | 3855092.07 | 1.11 | 29.19 | 218670.78 | 1836047.93
24 | Steel | (M)16 MM TMT Bars | TON | 241.13 | 62540 | 15080270.2 | 238.51 | 238.51 | 62507.23 | 14908600.07 | 238.47 | 236.1121 | 62700.41 | 14804324.85 | 2.62 | 5.0179 | 171670.13 | 275945.35
25 | Steel | (M)20 MM TMT Bars | TON | 168.92 | 62540 | 10564256.8 | 150.74 | 150.74 | 61028.17 | 9199386.9 | 150.74 | 157.64 | 60629.13 | 9557575.72 | 18.18 | 11.28 | 1364869.9 | 1006681.08
26 | Steel | (M)25 MM TMT Bars | TON | 263.22 | 62540 | 16461778.8 | 257.55 | 257.55 | 61726.56 | 15897674.64 | 257.55 | 248.19 | 61871.98 | 15356006.98 | 5.67 | 15.03 | 564104.16 | 1105771.82
27 | Steel | (M)32 MM TMT Bars | TON | 3.93 | 62540 | 245782.2 | 3.93 | 3.93 | 62874.24 | 247095.75 | 3.93 | 3.91 | 62605.56 | 244787.74 | 0 | 0.02 | -1313.55 | 994.46
28 | Steel | (M)8 MM TMT Bars | TON | 194.97 | 62000 | 12088140 | 149.05 | 149.05 | 64328.53 | 9588167.26 | 148.43 | 159.87 | 64037.88 | 10237736.39 | 45.92 | 35.1 | 2499972.74 | 1850403.61
29 | RCC | (L)RCC Labour | sq.ft | 198015 | 218.3 | 43226674.5 | 0 | 129133.987 | 203.57 | 26287300.04 | 129133.987 | 129133.987 | 203.57 | 26287300.04 | 68881.013 | 68881.013 | 16939374.47 | 16939374.46
30 | RCC | (L)RCC Retaining wall | sq.ft | 42420 | 153.4 | 6507228 | 0 | 11788.52 | 133.01 | 1568040.96 | 11788.52 | 11788.52 | 133.01 | 1568040.96 | 30631.48 | 30631.48 | 4939187.04 | 4939187.04
31 | rebaring | (L)10mm rebaring 200mm depth (HY 200R) | NOS | 234 | 141.6 | 33134.4 | 1 | 190 | 129.8 | 24662 | 190 | 190 | 129.8 | 24662 | 44 | 44 | 8472.4 | 8472.4
32 | rebaring | (L)12mm rebaring 200mm depth (HY 200R) | NOS | 41 | 147.5 | 6047.5 | 1 | 41 | 153.4 | 6289.4 | 41 | 41 | 153.4 | 6289.4 | 0 | 0 | -241.9 | -241.9
33 | rebaring | (L)16mm rebaring 200mm depth (HY 200R) | NOS | 220 | 265.5 | 58410 | 1 | 153 | 424.8 | 64994.4 | 153 | 153 | 424.8 | 64994.4 | 67 | 67 | -6584.4 | -6584.4
34 | rebaring | (L)20mm rebaring 200mm depth (HY 200R) | NOS | 15 | 472 | 7080 | 0 | 12 | 472 | 5664 | 12 | 12 | 472 | 5664 | 3 | 3 | 1416 | 1416
35 | rebaring | (L)8mm rebaring 200mm depth (HY 200R) | NOS | 16 | 129.8 | 2076.8 | 1 | 16 | 97.94 | 1567.04 | 16 | 16 | 97.94 | 1567.04 | 0 | 0 | 509.76 | 509.76
36 | site survey | (L)site survey full day | NOS | 1 | 750 | 750 | 0 | 1 | 7500 | 7500 | 1 | 1 | 7500 | 7500 | 0 | 0 | -6750 | -6750